## Portfolio Dashboard
Portfolio Finance Dashboard
Engagement Finance Toolkit -- synthetic data, as of 2025-08-15
Total Portfolio Budget |  |  | Total Actual $ to Date |  |  | Portfolio Utilization % | Engagements Over Budget | Open Exceptions | High-Severity Exceptions
6603130 |  |  | 5127914 |  |  | 77.65% | 0 | 64 | 19
Monthly Portfolio Trend
Month | Budgeted Hours | Actual Hours | Utilization % | Actual $ (Standard) | Actual $ (Recorded) | Realization %
2024-10-01 | 211.26 | 161.1 | 76.26% | 33665.5 | 33665.5 | 100%
2024-11-01 | 695.71 | 599.1 | 86.11% | 127456 | 127599 | 100.1%
2024-12-01 | 1210.85 | 1117.1 | 92.26% | 237530 | 237967.5 | 100.2%
2025-01-01 | 1592.92 | 1515.7 | 95.15% | 321468.5 | 320580.5 | 99.72%
2025-02-01 | 2160.24 | 2135.3 | 98.85% | 456569 | 457508 | 100.2%
2025-03-01 | 2610.86 | 2767.4 | 106% | 582630.5 | 585181.5 | 100.4%
2025-04-01 | 2803.77 | 3150.7 | 112.4% | 670385 | 670953 | 100.1%
2025-05-01 | 2886.81 | 3492.1 | 121% | 742682.5 | 743284.5 | 100.1%
2025-06-01 | 2766.21 | 3966.3 | 143.4% | 843966 | 848766.5 | 100.6%
2025-07-01 | 2510.16 | 3588.8 | 143% | 758340 | 759442.5 | 100.1%
2025-08-01 | 2212.15 | 1660.2 | 75.05% | 353221 | 353221 | 100%
Open Exceptions by Severity
Severity | Count | $ Impact
High | 19 | 152639
Medium | 28 | 70151.5
Low | 17 | 116848.32

## Engagement Summary
Engagement Portfolio Summary
Synthetic data, as of 2025-08-15 -- for portfolio demonstration only
Engagement ID | Client | Engagement Name | Contract Type | Engagement Leader | Start Date | End Date | Budgeted Hours | Budgeted $ | Contract Ceiling $ | Change Order $ | Approved Ceiling $ | Schedule % Elapsed | Actual Hours to Date | Actual $ to Date | Utilization % | % of Ceiling Consumed | Budget/Schedule Variance | Status | Open Exceptions | Total Exception $ Impact | Ceiling Basis $ to Date
ENG-001 | Commonwealth Department of Transportation | Highway Asset Management Program Support | Fixed-Fee | M. Alvarez | 2024-10-23 | 2025-05-18 | 2104 | 449785 | 449785 | 52794.37 | 502579.37 | 100% | 1772 | 381620 | 84.22% | 75.93% | -15.78% | Behind Pace / Under-Utilized | 4 | 10694.5 | 381620
ENG-002 | Bureau of Health & Human Services | Medicaid Eligibility System Modernization PMO | Fixed-Fee | R. Chen | 2024-11-06 | 2025-07-09 | 1159 | 246725 | 246725 | 0 | 246725 | 100% | 953.8 | 203218.5 | 82.3% | 82.37% | -17.7% | Behind Pace / Under-Utilized | 4 | 10036.5 | 203218.5
ENG-003 | Federal Logistics & Readiness Agency | Logistics Readiness ERP Modernization PMO | Cost-Plus-Fixed-Fee | M. Alvarez | 2025-02-13 | 2025-10-22 | 1277 | 272510 | 162229.64 | 0 | 162229.64 | 84.8% | 1068.6 | 225681.5 | 83.68% | 81.89% | -1.119% | On Track | 2 | 8394.5 | 132853.64
ENG-004 | Ashford County Government | County Financial Systems Upgrade Support | Cost-Plus-Fixed-Fee | M. Alvarez | 2024-11-02 | 2025-11-14 | 2894 | 614015 | 397488.71 | 59655.92 | 457144.63 | 83.3% | 1744 | 372266 | 60.26% | 49.28% | -23.04% | Behind Pace / Under-Utilized | 4 | 9749.5 | 225271.97
ENG-005 | Metro Regional Transit Authority | Capital Projects Cost Control Advisory | Fixed-Fee | R. Chen | 2025-03-02 | 2025-11-10 | 2810 | 593475 | 593475 | 0 | 593475 | 72.2% | 2385.5 | 505278 | 84.89% | 85.14% | 12.69% | On Track | 4 | 14848.5 | 505278
ENG-006 | Commonwealth Department of Transportation | Capital Program Financial Advisory | Cost-Plus-Fixed-Fee | R. Chen | 2024-12-05 | 2026-05-06 | 4106 | 870360 | 510577.09 | 0 | 510577.09 | 50% | 2462.7 | 522527.5 | 59.98% | 59.92% | 9.978% | On Track | 4 | 24633 | 305925.84
ENG-007 | Bureau of Health & Human Services | Provider Payment Integrity Review | Fixed-Fee | R. Chen | 2025-01-21 | 2025-04-22 | 236 | 50595 | 50595 | 4734.19 | 55329.19 | 100% | 205.3 | 42484.5 | 86.99% | 76.78% | -13.01% | On Track | 0 | 0 | 42484.5
ENG-008 | Federal Logistics & Readiness Agency | Supply Chain Cost Accounting Advisory | Time & Materials | R. Chen | 2025-04-29 | 2026-06-22 | 1194 | 256650 | 263798.86 | 55201.81 | 319000.67 | 28.4% | 1032 | 222334 | 86.43% | 69.7% | 58.03% | Trending Over Budget | 4 | 4153 | 222334
ENG-009 | Ashford County Government | Procurement Process Improvement Study | Cost-Plus-Fixed-Fee | D. Okoro | 2024-11-20 | 2025-06-13 | 2492 | 529510 | 319379.48 | 0 | 319379.48 | 100% | 2071.8 | 440190.5 | 83.14% | 80.55% | -16.86% | Behind Pace / Under-Utilized | 6 | 101264.06 | 257267.88
ENG-010 | Metro Regional Transit Authority | Fare System Financial Reconciliation Support | Time & Materials | S. Whitfield | 2025-05-21 | 2026-04-12 | 2748 | 583770 | 587107.14 | 0 | 587107.14 | 28.2% | 2484.9 | 529438 | 90.43% | 90.18% | 62.23% | Trending Over Budget | 5 | 75100.14 | 529438
ENG-011 | Commonwealth Department of Transportation | Fleet Maintenance Cost Optimization Study | Time & Materials | J. Patel | 2025-06-15 | 2026-09-09 | 2213 | 472045 | 498726.25 | 0 | 498726.25 | 12.7% | 1304.1 | 274820.5 | 58.93% | 55.1% | 46.23% | Trending Over Budget | 3 | 12081.5 | 274820.5
ENG-012 | Bureau of Health & Human Services | Benefits Program Financial Audit Support | Time & Materials | R. Chen | 2025-02-11 | 2025-11-22 | 1390 | 294840 | 322356.22 | 0 | 322356.22 | 76.1% | 1231.3 | 260508.5 | 88.58% | 80.81% | 12.48% | On Track | 4 | 9780.5 | 260508.5
ENG-013 | Federal Logistics & Readiness Agency | Acquisition Support Services | Fixed-Fee | J. Patel | 2025-02-03 | 2025-08-06 | 951 | 201140 | 201140 | 33951.09 | 235091.09 | 100% | 810.3 | 170888.5 | 85.21% | 72.69% | -14.79% | On Track | 2 | 3746 | 170888.5
ENG-014 | Ashford County Government | Budget Office Advisory Services | Time & Materials | R. Chen | 2025-02-06 | 2025-08-31 | 574 | 123310 | 130037.67 | 0 | 130037.67 | 100% | 423 | 90149.5 | 73.69% | 69.33% | -26.31% | Behind Pace / Under-Utilized | 4 | 6413.5 | 90149.5
ENG-015 | Metro Regional Transit Authority | Transit Asset Management Program Support | Cost-Plus-Fixed-Fee | R. Chen | 2024-12-15 | 2026-01-19 | 2152 | 447335 | 276292.78 | 53043.84 | 329336.62 | 68.8% | 1917.4 | 398188.5 | 89.1% | 73.24% | 20.3% | Trending Over Budget | 4 | 11046.5 | 241189.9
ENG-016 | Commonwealth Department of Transportation | Grants Compliance & Reporting Support | Time & Materials | D. Okoro | 2024-10-13 | 2025-07-11 | 1399 | 295805 | 306148.07 | 0 | 306148.07 | 100% | 1140.8 | 243827.5 | 81.54% | 79.64% | -18.46% | Behind Pace / Under-Utilized | 4 | 11663 | 243827.5
ENG-017 | Bureau of Health & Human Services | Case Management System Implementation Support | Time & Materials | S. Whitfield | 2025-01-25 | 2025-11-15 | 805 | 173260 | 176353.87 | 0 | 176353.87 | 79.1% | 654.7 | 140683.5 | 81.33% | 79.77% | 2.229% | On Track | 3 | 3598 | 140683.5
ENG-018 | Federal Logistics & Readiness Agency | Financial Systems Audit Readiness | Cost-Plus-Fixed-Fee | J. Patel | 2025-02-13 | 2025-08-31 | 603 | 128000 | 82503.54 | 0 | 82503.54 | 100% | 491.6 | 103809 | 81.53% | 75.43% | -18.47% | Behind Pace / Under-Utilized | 3 | 22436.12 | 62235.54

## Budget vs Actual
Budget vs Actual -- by Engagement, Role, Month
Synthetic data, as of 2025-08-15
Engagement ID | Client | Role | Month | Budgeted Hours | Actual Hours | Utilization % | Budgeted $ | Actual $ (Standard Rate) | Actual $ (Recorded Rate) | Rate Realization %
ENG-001 | Commonwealth Department of Transportation | Associate | 2024-10-01 | 47.2 | 43 | 91.1% | 7316.05 | 6665 | 6665 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2024-10-01 | 56.89 | 39.3 | 69.08% | 11947.1 | 8253 | 8253 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2024-10-01 | 26.7 | 18.6 | 69.66% | 7342.09 | 5115 | 5115 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2024-10-01 | 7.91 | 2.9 | 36.66% | 3045.61 | 1116.5 | 1116.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2024-11-01 | 80.71 | 74.3 | 92.06% | 12510.39 | 11516.5 | 11516.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2024-11-01 | 97.28 | 88.1 | 90.56% | 20429.43 | 18501 | 18501 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2024-11-01 | 45.65 | 44.7 | 97.92% | 12554.92 | 12292.5 | 12292.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2024-11-01 | 13.53 | 12.7 | 93.87% | 5207.97 | 4889.5 | 4889.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2024-12-01 | 107.59 | 73.1 | 67.94% | 16675.93 | 11330.5 | 11330.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2024-12-01 | 129.67 | 107.2 | 82.67% | 27231.74 | 22512 | 22512 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2024-12-01 | 60.86 | 53.7 | 88.24% | 16735.28 | 14767.5 | 14767.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2024-12-01 | 18.03 | 17.6 | 97.62% | 6942.04 | 6776 | 6776 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2025-01-01 | 122.5 | 104.6 | 85.39% | 18987.63 | 16213 | 16213 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2025-01-01 | 147.65 | 129.7 | 87.84% | 31006.73 | 27237 | 27237 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2025-01-01 | 69.29 | 64.4 | 92.94% | 19055.21 | 17710 | 17710 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2025-01-01 | 20.53 | 16.8 | 81.83% | 7904.38 | 6468 | 6468 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2025-02-01 | 122.5 | 90.4 | 73.8% | 18987.63 | 14012 | 14012 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2025-02-01 | 147.65 | 128.9 | 87.3% | 31006.73 | 27069 | 27069 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2025-02-01 | 69.29 | 67.3 | 97.13% | 19055.21 | 18507.5 | 18507.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2025-02-01 | 20.53 | 18.2 | 88.65% | 7904.38 | 7007 | 7007 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2025-03-01 | 107.59 | 88.2 | 81.98% | 16675.93 | 13671 | 13671 | 100%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2025-03-01 | 129.67 | 111.6 | 86.06% | 27231.74 | 23436 | 23436 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2025-03-01 | 60.86 | 60.9 | 100.1% | 16735.28 | 16747.5 | 16747.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2025-03-01 | 18.03 | 14 | 77.65% | 6942.04 | 5390 | 5390 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2025-04-01 | 80.71 | 62.1 | 76.94% | 12510.39 | 9625.5 | 10959.5 | 113.9%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2025-04-01 | 97.28 | 77.1 | 79.26% | 20429.43 | 16191 | 16191 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2025-04-01 | 45.65 | 42.3 | 92.66% | 12554.92 | 11632.5 | 11632.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2025-04-01 | 13.53 | 10.1 | 74.65% | 5207.97 | 3888.5 | 3888.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Associate | 2025-05-01 | 47.2 | 41.1 | 87.08% | 7316.05 | 6370.5 | 7030.5 | 110.4%
ENG-001 | Commonwealth Department of Transportation | Consultant | 2025-05-01 | 56.89 | 42.9 | 75.41% | 11947.1 | 9009 | 9009 | 100%
ENG-001 | Commonwealth Department of Transportation | Manager | 2025-05-01 | 26.7 | 21.7 | 81.27% | 7342.09 | 5967.5 | 5967.5 | 100%
ENG-001 | Commonwealth Department of Transportation | Partner | 2025-05-01 | 7.91 | 4.5 | 56.89% | 3045.61 | 1732.5 | 945 | 54.55%
ENG-002 | Bureau of Health & Human Services | Associate | 2024-11-01 | 22.18 | 21.5 | 96.93% | 3437.14 | 3332.5 | 3332.5 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2024-11-01 | 30.53 | 28.7 | 94.01% | 6412.19 | 6027 | 6027 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2024-11-01 | 10.33 | 9.6 | 92.93% | 2841.54 | 2640 | 2640 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2024-11-01 | 4.24 | 3.9 | 91.98% | 1631.49 | 1501.5 | 1501.5 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2024-12-01 | 36.06 | 36.1 | 100.1% | 5589.5 | 5595.5 | 5595.5 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2024-12-01 | 49.66 | 39.4 | 79.34% | 10427.57 | 8274 | 8274 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2024-12-01 | 16.8 | 10.9 | 64.88% | 4620.94 | 2997.5 | 2997.5 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2024-12-01 | 6.89 | 2.2 | 31.93% | 2653.15 | 847 | 847 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-01-01 | 47.83 | 39.8 | 83.21% | 7414.19 | 6169 | 6169 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-01-01 | 65.86 | 44.7 | 67.87% | 13831.64 | 9387 | 9387 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-01-01 | 22.29 | 18.5 | 83% | 6129.45 | 5087.5 | 5087.5 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-01-01 | 9.14 | 9.1 | 99.56% | 3519.27 | 3503.5 | 3503.5 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-02-01 | 55.7 | 44.8 | 80.43% | 8633.41 | 6944 | 6944 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-02-01 | 76.7 | 64.4 | 83.96% | 16106.16 | 13524 | 13524 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-02-01 | 25.95 | 24.4 | 94.03% | 7137.4 | 6710 | 6710 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-02-01 | 10.64 | 7.7 | 72.37% | 4097.99 | 2964.5 | 2964.5 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-03-01 | 58.46 | 46.4 | 79.37% | 9061.54 | 7192 | 7192 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-03-01 | 80.5 | 72.4 | 89.94% | 16904.87 | 15204 | 15204 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-03-01 | 27.24 | 27 | 99.12% | 7491.34 | 7425 | 8074 | 108.7%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-03-01 | 11.17 | 8.9 | 79.68% | 4301.21 | 3426.5 | 3426.5 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-04-01 | 55.7 | 41.8 | 75.04% | 8633.41 | 6479 | 6479 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-04-01 | 76.7 | 68.1 | 88.79% | 16106.16 | 14301 | 14301 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-04-01 | 25.95 | 24.7 | 95.18% | 7137.4 | 6792.5 | 6792.5 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-04-01 | 10.64 | 7.8 | 73.31% | 4097.99 | 3003 | 3003 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-05-01 | 47.83 | 39.1 | 81.75% | 7414.19 | 6060.5 | 6060.5 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-05-01 | 65.86 | 52.3 | 79.41% | 13831.64 | 10983 | 10983 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-05-01 | 22.29 | 19.1 | 85.69% | 6129.45 | 5252.5 | 5252.5 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-05-01 | 9.14 | 6.2 | 67.83% | 3519.27 | 2387 | 2387 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-06-01 | 36.06 | 24 | 66.56% | 5589.5 | 3720 | 3720 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-06-01 | 49.66 | 45.1 | 90.82% | 10427.57 | 9471 | 9471 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-06-01 | 16.8 | 8.6 | 51.19% | 4620.94 | 2365 | 2365 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-06-01 | 6.89 | 5.9 | 85.63% | 2653.15 | 2271.5 | 2271.5 | 100%
ENG-002 | Bureau of Health & Human Services | Associate | 2025-07-01 | 22.18 | 12.2 | 55% | 3437.14 | 1891 | 1891 | 100%
ENG-002 | Bureau of Health & Human Services | Consultant | 2025-07-01 | 30.53 | 24 | 78.61% | 6412.19 | 5040 | 5040 | 100%
ENG-002 | Bureau of Health & Human Services | Manager | 2025-07-01 | 10.33 | 10.3 | 99.71% | 2841.54 | 2832.5 | 2832.5 | 100%
ENG-002 | Bureau of Health & Human Services | Partner | 2025-07-01 | 4.24 | 4.2 | 99.06% | 1631.49 | 1617 | 1617 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-02-01 | 23.92 | 24.5 | 102.4% | 3707.07 | 3797.5 | 3797.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-02-01 | 33.96 | 33.8 | 99.53% | 7131.43 | 7098 | 7098 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-02-01 | 11.61 | 15.3 | 131.8% | 3192.75 | 4207.5 | 4207.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-02-01 | 4.64 | 5.5 | 118.5% | 1787.94 | 2117.5 | 2117.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-03-01 | 38.89 | 51.1 | 131.4% | 6028.47 | 7920.5 | 7920.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-03-01 | 55.22 | 70.5 | 127.7% | 11597.2 | 14805 | 14805 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-03-01 | 18.88 | 24.4 | 129.2% | 5192.07 | 6710 | 6710 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-03-01 | 7.55 | 8 | 106% | 2907.56 | 3080 | 3080 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-04-01 | 51.59 | 65.3 | 126.6% | 7996.45 | 10121.5 | 10121.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-04-01 | 73.25 | 88.6 | 121% | 15383.1 | 18606 | 18606 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-04-01 | 25.04 | 28.2 | 112.6% | 6887.02 | 7755 | 7755 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-04-01 | 10.02 | 10.1 | 100.8% | 3856.73 | 3888.5 | 3888.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-05-01 | 60.07 | 65.2 | 108.5% | 9311.42 | 10106 | 10106 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-05-01 | 85.3 | 88.1 | 103.3% | 17912.75 | 18501 | 18501 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-05-01 | 29.16 | 36 | 123.5% | 8019.55 | 9900 | 9900 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-05-01 | 11.66 | 11 | 94.34% | 4490.95 | 4235 | 4235 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-06-01 | 63.05 | 72.5 | 115% | 9773.18 | 11237.5 | 11237.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-06-01 | 89.53 | 99.1 | 110.7% | 18801.05 | 20811 | 20811 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-06-01 | 30.61 | 21.5 | 70.24% | 8417.24 | 5912.5 | 5912.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-06-01 | 12.24 | 10.5 | 85.78% | 4713.65 | 4042.5 | 4042.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-07-01 | 60.07 | 48.5 | 80.74% | 9311.42 | 7517.5 | 7517.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-07-01 | 85.3 | 70.7 | 82.88% | 17912.75 | 14847 | 14847 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-07-01 | 29.16 | 27.7 | 94.99% | 8019.55 | 7617.5 | 7617.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-07-01 | 11.66 | 9.9 | 84.91% | 4490.95 | 3811.5 | 3811.5 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Associate | 2025-08-01 | 51.59 | 29.2 | 56.6% | 7996.45 | 4526 | 4526 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Consultant | 2025-08-01 | 73.25 | 37.7 | 51.47% | 15383.1 | 7917 | 7917 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Manager | 2025-08-01 | 25.04 | 13.2 | 52.72% | 6887.02 | 3630 | 3630 | 100%
ENG-003 | Federal Logistics & Readiness Agency | Partner | 2025-08-01 | 10.02 | 2.5 | 24.95% | 3856.73 | 962.5 | 962.5 | 100%
ENG-004 | Ashford County Government | Associate | 2024-11-01 | 40.43 | 25.5 | 63.07% | 6265.97 | 3952.5 | 3952.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2024-11-01 | 47.62 | 45.2 | 94.92% | 10000.62 | 9492 | 9492 | 100%
ENG-004 | Ashford County Government | Manager | 2024-11-01 | 18.52 | 12.1 | 65.33% | 5093.51 | 3327.5 | 3152 | 94.73%
ENG-004 | Ashford County Government | Partner | 2024-11-01 | 7.24 | 6.9 | 95.3% | 2785.75 | 2656.5 | 2656.5 | 100%
ENG-004 | Ashford County Government | Associate | 2024-12-01 | 57.55 | 45.4 | 78.89% | 8919.75 | 7037 | 7037 | 100%
ENG-004 | Ashford County Government | Consultant | 2024-12-01 | 67.79 | 68.2 | 100.6% | 14236.11 | 14322 | 14322 | 100%
ENG-004 | Ashford County Government | Manager | 2024-12-01 | 26.37 | 22.9 | 86.84% | 7250.72 | 6297.5 | 6297.5 | 100%
ENG-004 | Ashford County Government | Partner | 2024-12-01 | 10.3 | 10.7 | 103.9% | 3965.58 | 4119.5 | 4119.5 | 100%
ENG-004 | Ashford County Government | Associate | 2025-01-01 | 73.5 | 67.9 | 92.38% | 11392.68 | 10524.5 | 10524.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-01-01 | 86.59 | 76.1 | 87.89% | 18182.95 | 15981 | 15981 | 100%
ENG-004 | Ashford County Government | Manager | 2025-01-01 | 33.68 | 28.8 | 85.51% | 9260.93 | 7920 | 7920 | 100%
ENG-004 | Ashford County Government | Partner | 2025-01-01 | 13.16 | 8.2 | 62.31% | 5065 | 3157 | 3157 | 100%
ENG-004 | Ashford County Government | Associate | 2025-02-01 | 87.2 | 64.9 | 74.43% | 13516.23 | 10059.5 | 10059.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-02-01 | 102.72 | 93.9 | 91.41% | 21572.18 | 19719 | 19719 | 100%
ENG-004 | Ashford County Government | Manager | 2025-02-01 | 39.95 | 42.5 | 106.4% | 10987.13 | 11687.5 | 11687.5 | 100%
ENG-004 | Ashford County Government | Partner | 2025-02-01 | 15.61 | 10.6 | 67.91% | 6009.1 | 4081 | 4081 | 100%
ENG-004 | Ashford County Government | Associate | 2025-03-01 | 97.71 | 81.9 | 83.82% | 15145.68 | 12694.5 | 12694.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-03-01 | 115.11 | 97 | 84.27% | 24172.83 | 20370 | 21017.5 | 103.2%
ENG-004 | Ashford County Government | Manager | 2025-03-01 | 44.77 | 38.8 | 86.67% | 12311.69 | 10670 | 10670 | 100%
ENG-004 | Ashford County Government | Partner | 2025-03-01 | 17.49 | 14.9 | 85.19% | 6733.53 | 5736.5 | 5736.5 | 100%
ENG-004 | Ashford County Government | Associate | 2025-04-01 | 104.32 | 78.3 | 75.06% | 16170 | 12136.5 | 12136.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-04-01 | 122.89 | 93 | 75.68% | 25807.67 | 19530 | 19530 | 100%
ENG-004 | Ashford County Government | Manager | 2025-04-01 | 47.8 | 45.9 | 96.03% | 13144.34 | 12622.5 | 12622.5 | 100%
ENG-004 | Ashford County Government | Partner | 2025-04-01 | 18.67 | 14.3 | 76.59% | 7188.92 | 5505.5 | 5505.5 | 100%
ENG-004 | Ashford County Government | Associate | 2025-05-01 | 106.58 | 66.6 | 62.49% | 16519.38 | 10323 | 10323 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-05-01 | 125.55 | 98.2 | 78.22% | 26365.28 | 20622 | 21182 | 102.7%
ENG-004 | Ashford County Government | Manager | 2025-05-01 | 48.83 | 32.4 | 66.35% | 13428.35 | 8910 | 8910 | 100%
ENG-004 | Ashford County Government | Partner | 2025-05-01 | 19.08 | 14.1 | 73.9% | 7344.25 | 5428.5 | 5428.5 | 100%
ENG-004 | Ashford County Government | Associate | 2025-06-01 | 104.32 | 62.2 | 59.62% | 16170 | 9641 | 9641 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-06-01 | 122.89 | 78.1 | 63.55% | 25807.67 | 16401 | 16401 | 100%
ENG-004 | Ashford County Government | Manager | 2025-06-01 | 47.8 | 31.2 | 65.27% | 13144.34 | 8580 | 8580 | 100%
ENG-004 | Ashford County Government | Partner | 2025-06-01 | 18.67 | 11.6 | 62.13% | 7188.92 | 4466 | 4466 | 100%
ENG-004 | Ashford County Government | Associate | 2025-07-01 | 97.71 | 59.9 | 61.3% | 15145.68 | 9284.5 | 9284.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-07-01 | 115.11 | 63 | 54.73% | 24172.83 | 13230 | 13230 | 100%
ENG-004 | Ashford County Government | Manager | 2025-07-01 | 44.77 | 27.4 | 61.2% | 12311.69 | 7535 | 7535 | 100%
ENG-004 | Ashford County Government | Partner | 2025-07-01 | 17.49 | 10.1 | 57.75% | 6733.53 | 3888.5 | 3888.5 | 100%
ENG-004 | Ashford County Government | Associate | 2025-08-01 | 87.2 | 36.5 | 41.86% | 13516.23 | 5657.5 | 5657.5 | 100%
ENG-004 | Ashford County Government | Consultant | 2025-08-01 | 102.72 | 34.3 | 33.39% | 21572.18 | 7203 | 7203 | 100%
ENG-004 | Ashford County Government | Manager | 2025-08-01 | 39.95 | 17.6 | 44.06% | 10987.13 | 4840 | 4840 | 100%
ENG-004 | Ashford County Government | Partner | 2025-08-01 | 15.61 | 6.9 | 44.2% | 6009.1 | 2656.5 | 2656.5 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-03-01 | 54.8 | 58.2 | 106.2% | 8493.86 | 9021 | 9021 | 100%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-03-01 | 75.64 | 99.9 | 132.1% | 15884.2 | 20979 | 20979 | 100%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-03-01 | 22.81 | 23.5 | 103% | 6273.74 | 6462.5 | 6462.5 | 100%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-03-01 | 9.87 | 10.6 | 107.4% | 3799.37 | 4081 | 4081 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-04-01 | 89.11 | 149.9 | 168.2% | 13812.8 | 23234.5 | 23234.5 | 100%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-04-01 | 123 | 198.7 | 161.5% | 25831.03 | 41727 | 41727 | 100%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-04-01 | 37.1 | 69.9 | 188.4% | 10202.42 | 19222.5 | 19222.5 | 100%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-04-01 | 16.05 | 25.7 | 160.1% | 6178.57 | 9894.5 | 9894.5 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-05-01 | 118.21 | 175.5 | 148.5% | 18321.97 | 27202.5 | 27202.5 | 100%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-05-01 | 163.16 | 227.6 | 139.5% | 34263.54 | 47796 | 47796 | 100%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-05-01 | 49.21 | 75.5 | 153.4% | 13532.99 | 20762.5 | 20762.5 | 100%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-05-01 | 21.29 | 39.4 | 185.1% | 8195.55 | 15169 | 15169 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-06-01 | 137.64 | 191 | 138.8% | 21334.91 | 29605 | 29803 | 100.7%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-06-01 | 189.99 | 261.4 | 137.6% | 39897.97 | 54894 | 54718 | 99.68%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-06-01 | 57.3 | 80.9 | 141.2% | 15758.41 | 22247.5 | 22665.5 | 101.9%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-06-01 | 24.79 | 39.4 | 158.9% | 9543.26 | 15169 | 15169 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-07-01 | 144.47 | 162.2 | 112.3% | 22392.91 | 25141 | 25141 | 100%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-07-01 | 199.41 | 201.2 | 100.9% | 41876.52 | 42252 | 42252 | 100%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-07-01 | 60.14 | 59.8 | 99.43% | 16539.87 | 16445 | 16445 | 100%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-07-01 | 26.02 | 23.5 | 90.32% | 10016.51 | 9047.5 | 9047.5 | 100%
ENG-005 | Metro Regional Transit Authority | Associate | 2025-08-01 | 137.64 | 69.8 | 50.71% | 21334.91 | 10819 | 10819 | 100%
ENG-005 | Metro Regional Transit Authority | Consultant | 2025-08-01 | 189.99 | 101.7 | 53.53% | 39897.97 | 21357 | 21357 | 100%
ENG-005 | Metro Regional Transit Authority | Manager | 2025-08-01 | 57.3 | 24.8 | 43.28% | 15758.41 | 6820 | 6820 | 100%
ENG-005 | Metro Regional Transit Authority | Partner | 2025-08-01 | 24.79 | 15.4 | 62.12% | 9543.26 | 5929 | 5929 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2024-12-01 | 40.13 | 59.8 | 149% | 6220.14 | 9269 | 9269 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2024-12-01 | 50.76 | 62.3 | 122.7% | 10659.25 | 13083 | 13083 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2024-12-01 | 16.46 | 18.5 | 112.4% | 4526.89 | 5087.5 | 5087.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2024-12-01 | 7.8 | 11.6 | 148.7% | 3001.47 | 4466 | 4466 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-01-01 | 52.2 | 85.1 | 163% | 8090.42 | 13190.5 | 13190.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-01-01 | 66.02 | 101.8 | 154.2% | 13864.28 | 21378 | 21378 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-01-01 | 21.41 | 31.5 | 147.1% | 5888.03 | 8662.5 | 8110.5 | 93.63%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-01-01 | 10.14 | 16.9 | 166.7% | 3903.96 | 6506.5 | 6506.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-02-01 | 63.85 | 93.5 | 146.4% | 9897 | 14492.5 | 15056.5 | 103.9%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-02-01 | 80.76 | 132 | 163.4% | 16960.17 | 27720 | 27351.5 | 98.67%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-02-01 | 26.19 | 44.5 | 169.9% | 7202.83 | 12237.5 | 12237.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-02-01 | 12.4 | 17.8 | 143.5% | 4775.71 | 6853 | 6853 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-03-01 | 74.7 | 131.6 | 176.2% | 11578.38 | 20398 | 20398 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-03-01 | 94.48 | 164.5 | 174.1% | 19841.49 | 34545 | 34336 | 99.39%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-03-01 | 30.64 | 41.6 | 135.8% | 8426.5 | 11440 | 11440 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-03-01 | 14.51 | 20.6 | 142% | 5587.04 | 7931 | 7931 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-04-01 | 84.37 | 123.2 | 146% | 13077.29 | 19096 | 19096 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-04-01 | 106.71 | 153.6 | 143.9% | 22410.12 | 32256 | 32405.5 | 100.5%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-04-01 | 34.61 | 63.3 | 182.9% | 9517.37 | 17407.5 | 17167.5 | 98.62%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-04-01 | 16.39 | 25.8 | 157.4% | 6310.33 | 9933 | 9933 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-05-01 | 92.53 | 113.4 | 122.6% | 14342.68 | 17577 | 17577 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-05-01 | 117.04 | 168.3 | 143.8% | 24578.59 | 35343 | 35343 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-05-01 | 37.96 | 48.8 | 128.6% | 10438.3 | 13420 | 12556 | 93.56%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-05-01 | 17.98 | 29.2 | 162.4% | 6920.93 | 11242 | 11242 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-06-01 | 98.91 | 119.2 | 120.5% | 15331.48 | 18476 | 18476 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-06-01 | 125.11 | 141.7 | 113.3% | 26273.05 | 29757 | 29757 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-06-01 | 40.57 | 49.5 | 122% | 11157.92 | 13612.5 | 13612.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-06-01 | 19.22 | 20.8 | 108.2% | 7398.06 | 8008 | 8008 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-07-01 | 103.29 | 84.3 | 81.61% | 16009.99 | 13066.5 | 13066.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-07-01 | 130.65 | 104.8 | 80.21% | 27435.8 | 22008 | 22008 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-07-01 | 42.37 | 25.8 | 60.89% | 11651.73 | 7095 | 7095 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-07-01 | 20.07 | 16.7 | 83.21% | 7725.48 | 6429.5 | 6429.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Associate | 2025-08-01 | 105.52 | 43.9 | 41.6% | 16355.13 | 6804.5 | 6804.5 | 100%
ENG-006 | Commonwealth Department of Transportation | Consultant | 2025-08-01 | 133.46 | 64 | 47.95% | 28027.25 | 13440 | 13440 | 100%
ENG-006 | Commonwealth Department of Transportation | Manager | 2025-08-01 | 43.28 | 21.2 | 48.98% | 11902.92 | 5830 | 5830 | 100%
ENG-006 | Commonwealth Department of Transportation | Partner | 2025-08-01 | 20.5 | 11.6 | 56.59% | 7892.02 | 4466 | 4466 | 100%
ENG-007 | Bureau of Health & Human Services | Associate | 2025-01-01 | 11.56 | 7.7 | 66.61% | 1791.71 | 1193.5 | 1193.5 | 100%
ENG-007 | Bureau of Health & Human Services | Consultant | 2025-01-01 | 15.07 | 13.2 | 87.59% | 3164.93 | 2772 | 2772 | 100%
ENG-007 | Bureau of Health & Human Services | Manager | 2025-01-01 | 5.41 | 5.8 | 107.2% | 1488.82 | 1595 | 1595 | 100%
ENG-007 | Bureau of Health & Human Services | Partner | 2025-01-01 | 2.49 | 2.7 | 108.4% | 957.67 | 1039.5 | 1039.5 | 100%
ENG-007 | Bureau of Health & Human Services | Associate | 2025-02-01 | 27.94 | 28.4 | 101.6% | 4330.79 | 4402 | 4402 | 100%
ENG-007 | Bureau of Health & Human Services | Consultant | 2025-02-01 | 36.43 | 32.7 | 89.76% | 7650.07 | 6867 | 6867 | 100%
ENG-007 | Bureau of Health & Human Services | Manager | 2025-02-01 | 13.09 | 7.3 | 55.77% | 3598.68 | 2007.5 | 2007.5 | 100%
ENG-007 | Bureau of Health & Human Services | Partner | 2025-02-01 | 6.01 | 3.3 | 54.91% | 2314.83 | 1270.5 | 1270.5 | 100%
ENG-007 | Bureau of Health & Human Services | Associate | 2025-03-01 | 27.94 | 27.6 | 98.78% | 4330.79 | 4278 | 4278 | 100%
ENG-007 | Bureau of Health & Human Services | Consultant | 2025-03-01 | 36.43 | 32.4 | 88.94% | 7650.07 | 6804 | 6804 | 100%
ENG-007 | Bureau of Health & Human Services | Manager | 2025-03-01 | 13.09 | 5.2 | 39.72% | 3598.68 | 1430 | 1430 | 100%
ENG-007 | Bureau of Health & Human Services | Partner | 2025-03-01 | 6.01 | 3.3 | 54.91% | 2314.83 | 1270.5 | 1270.5 | 100%
ENG-007 | Bureau of Health & Human Services | Associate | 2025-04-01 | 11.56 | 12.5 | 108.1% | 1791.71 | 1937.5 | 1937.5 | 100%
ENG-007 | Bureau of Health & Human Services | Consultant | 2025-04-01 | 15.07 | 16.3 | 108.2% | 3164.93 | 3423 | 3423 | 100%
ENG-007 | Bureau of Health & Human Services | Manager | 2025-04-01 | 5.41 | 4.2 | 77.63% | 1488.82 | 1155 | 1155 | 100%
ENG-007 | Bureau of Health & Human Services | Partner | 2025-04-01 | 2.49 | 2.7 | 108.4% | 957.67 | 1039.5 | 1039.5 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Associate | 2025-04-01 | 13.85 | 33.6 | 242.6% | 2147.3 | 5208 | 5208 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Consultant | 2025-04-01 | 16.26 | 57.9 | 356.1% | 3414.27 | 12159 | 12159 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Manager | 2025-04-01 | 7.69 | 17.6 | 228.9% | 2114.44 | 4840 | 4840 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Partner | 2025-04-01 | 2.64 | 9.4 | 356.1% | 1017.17 | 3619 | 3619 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Associate | 2025-05-01 | 18.9 | 86.6 | 458.2% | 2929.19 | 13423 | 13423 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Consultant | 2025-05-01 | 22.18 | 99.5 | 448.6% | 4657.49 | 20895 | 20895 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Manager | 2025-05-01 | 10.49 | 40.4 | 385.1% | 2884.37 | 11110 | 11110 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Partner | 2025-05-01 | 3.6 | 18.2 | 505.6% | 1387.55 | 7007 | 7007 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Associate | 2025-06-01 | 23.69 | 104 | 439% | 3671.86 | 16120 | 16120 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Consultant | 2025-06-01 | 27.8 | 121.6 | 437.4% | 5838.38 | 25536 | 26131 | 102.3%
ENG-008 | Federal Logistics & Readiness Agency | Manager | 2025-06-01 | 13.15 | 59 | 448.7% | 3615.68 | 16225 | 16225 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Partner | 2025-06-01 | 4.52 | 22.6 | 500% | 1739.35 | 8701 | 8701 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Associate | 2025-07-01 | 27.99 | 96.9 | 346.2% | 4338.09 | 15019.5 | 15019.5 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Consultant | 2025-07-01 | 32.85 | 98 | 298.3% | 6897.7 | 20580 | 20580 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Manager | 2025-07-01 | 15.53 | 35.8 | 230.5% | 4271.72 | 9845 | 9845 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Partner | 2025-07-01 | 5.34 | 20.3 | 380.1% | 2054.94 | 7815.5 | 7815.5 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Associate | 2025-08-01 | 31.58 | 30.6 | 96.9% | 4894.47 | 4743 | 4743 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Consultant | 2025-08-01 | 37.06 | 51 | 137.6% | 7782.36 | 10710 | 10710 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Manager | 2025-08-01 | 17.53 | 21.7 | 123.8% | 4819.58 | 5967.5 | 5967.5 | 100%
ENG-008 | Federal Logistics & Readiness Agency | Partner | 2025-08-01 | 6.02 | 7.3 | 121.3% | 2318.49 | 2810.5 | 2810.5 | 100%
ENG-009 | Ashford County Government | Associate | 2024-11-01 | 55.05 | 52.7 | 95.73% | 8531.99 | 8168.5 | 8168.5 | 100%
ENG-009 | Ashford County Government | Consultant | 2024-11-01 | 72.78 | 59.3 | 81.48% | 15283.42 | 12453 | 12771.5 | 102.6%
ENG-009 | Ashford County Government | Manager | 2024-11-01 | 26.76 | 14.2 | 53.06% | 7360.22 | 3905 | 3905 | 100%
ENG-009 | Ashford County Government | Partner | 2024-11-01 | 9.69 | 9.7 | 100.1% | 3730.87 | 3734.5 | 3734.5 | 100%
ENG-009 | Ashford County Government | Associate | 2024-12-01 | 94.13 | 86.7 | 92.11% | 14589.63 | 13438.5 | 13438.5 | 100%
ENG-009 | Ashford County Government | Consultant | 2024-12-01 | 124.45 | 111.2 | 89.35% | 26134.52 | 23352 | 23352 | 100%
ENG-009 | Ashford County Government | Manager | 2024-12-01 | 45.77 | 34.1 | 74.5% | 12585.92 | 9377.5 | 9377.5 | 100%
ENG-009 | Ashford County Government | Partner | 2024-12-01 | 16.57 | 16.6 | 100.2% | 6379.76 | 6391 | 6391 | 100%
ENG-009 | Ashford County Government | Associate | 2025-01-01 | 125.47 | 110.8 | 88.31% | 19447.49 | 17174 | 17174 | 100%
ENG-009 | Ashford County Government | Consultant | 2025-01-01 | 165.89 | 140.1 | 84.45% | 34836.43 | 29421 | 29421 | 100%
ENG-009 | Ashford County Government | Manager | 2025-01-01 | 61.01 | 50.6 | 82.94% | 16776.6 | 13915 | 13579 | 97.59%
ENG-009 | Ashford County Government | Partner | 2025-01-01 | 22.09 | 19.1 | 86.46% | 8504 | 7353.5 | 7353.5 | 100%
ENG-009 | Ashford County Government | Associate | 2025-02-01 | 142.86 | 115.6 | 80.92% | 22143.39 | 17918 | 17918 | 100%
ENG-009 | Ashford County Government | Consultant | 2025-02-01 | 188.88 | 144.9 | 76.72% | 39665.62 | 30429 | 30429 | 100%
ENG-009 | Ashford County Government | Manager | 2025-02-01 | 69.46 | 58 | 83.5% | 19102.26 | 15950 | 15950 | 100%
ENG-009 | Ashford County Government | Partner | 2025-02-01 | 25.15 | 20.8 | 82.7% | 9682.87 | 8008 | 8008 | 100%
ENG-009 | Ashford County Government | Associate | 2025-03-01 | 142.86 | 123 | 86.1% | 22143.39 | 19065 | 19263 | 101%
ENG-009 | Ashford County Government | Consultant | 2025-03-01 | 188.88 | 150.8 | 79.84% | 39665.62 | 31668 | 32006 | 101.1%
ENG-009 | Ashford County Government | Manager | 2025-03-01 | 69.46 | 56.5 | 81.34% | 19102.26 | 15537.5 | 15537.5 | 100%
ENG-009 | Ashford County Government | Partner | 2025-03-01 | 25.15 | 24.4 | 97.02% | 9682.87 | 9394 | 9394 | 100%
ENG-009 | Ashford County Government | Associate | 2025-04-01 | 125.47 | 100.1 | 79.78% | 19447.49 | 15515.5 | 15515.5 | 100%
ENG-009 | Ashford County Government | Consultant | 2025-04-01 | 165.89 | 142 | 85.6% | 34836.43 | 29820 | 29605.5 | 99.28%
ENG-009 | Ashford County Government | Manager | 2025-04-01 | 61.01 | 46.9 | 76.87% | 16776.6 | 12897.5 | 13414.5 | 104%
ENG-009 | Ashford County Government | Partner | 2025-04-01 | 22.09 | 14.5 | 65.64% | 8504 | 5582.5 | 5582.5 | 100%
ENG-009 | Ashford County Government | Associate | 2025-05-01 | 94.13 | 83.7 | 88.92% | 14589.63 | 12973.5 | 12973.5 | 100%
ENG-009 | Ashford County Government | Consultant | 2025-05-01 | 124.45 | 107.9 | 86.7% | 26134.52 | 22659 | 22230 | 98.11%
ENG-009 | Ashford County Government | Manager | 2025-05-01 | 45.77 | 40.6 | 88.7% | 12585.92 | 11165 | 11165 | 100%
ENG-009 | Ashford County Government | Partner | 2025-05-01 | 16.57 | 16.6 | 100.2% | 6379.76 | 6391 | 6391 | 100%
ENG-009 | Ashford County Government | Associate | 2025-06-01 | 55.05 | 39.5 | 71.75% | 8531.99 | 6122.5 | 6122.5 | 100%
ENG-009 | Ashford County Government | Consultant | 2025-06-01 | 72.78 | 44.5 | 61.14% | 15283.42 | 9345 | 9345 | 100%
ENG-009 | Ashford County Government | Manager | 2025-06-01 | 26.76 | 26.8 | 100.1% | 7360.22 | 7370 | 7370 | 100%
ENG-009 | Ashford County Government | Partner | 2025-06-01 | 9.69 | 9.6 | 99.07% | 3730.87 | 3696 | 3696 | 100%
ENG-010 | Metro Regional Transit Authority | Associate | 2025-05-01 | 39.22 | 119.8 | 305.5% | 6079.04 | 18569 | 18904.5 | 101.8%
ENG-010 | Metro Regional Transit Authority | Consultant | 2025-05-01 | 52.52 | 156.3 | 297.6% | 11029.39 | 32823 | 32823 | 100%
ENG-010 | Metro Regional Transit Authority | Manager | 2025-05-01 | 18.82 | 60.8 | 323.1% | 5175.11 | 16720 | 16720 | 100%
ENG-010 | Metro Regional Transit Authority | Partner | 2025-05-01 | 6.97 | 24.2 | 347.2% | 2684 | 9317 | 9317 | 100%
ENG-010 | Metro Regional Transit Authority | Associate | 2025-06-01 | 57.3 | 288 | 502.6% | 8881.58 | 44640 | 45996 | 103%
ENG-010 | Metro Regional Transit Authority | Consultant | 2025-06-01 | 76.73 | 409.7 | 534% | 16114.13 | 86037 | 85668.5 | 99.57%
ENG-010 | Metro Regional Transit Authority | Manager | 2025-06-01 | 27.49 | 136.9 | 498% | 7560.92 | 37647.5 | 36915.5 | 98.06%
ENG-010 | Metro Regional Transit Authority | Partner | 2025-06-01 | 10.19 | 51 | 500.5% | 3921.37 | 19635 | 19635 | 100%
ENG-010 | Metro Regional Transit Authority | Associate | 2025-07-01 | 73.92 | 294.2 | 398% | 11457.08 | 45601 | 46033 | 100.9%
ENG-010 | Metro Regional Transit Authority | Consultant | 2025-07-01 | 98.99 | 387.7 | 391.7% | 20786.93 | 81417 | 81048.5 | 99.55%
ENG-010 | Metro Regional Transit Authority | Manager | 2025-07-01 | 35.47 | 141.9 | 400.1% | 9753.45 | 39022.5 | 39253.5 | 100.6%
ENG-010 | Metro Regional Transit Authority | Partner | 2025-07-01 | 13.14 | 54.5 | 414.8% | 5058.49 | 20982.5 | 20982.5 | 100%
ENG-010 | Metro Regional Transit Authority | Associate | 2025-08-01 | 87.72 | 115.5 | 131.7% | 13596.87 | 17902.5 | 17902.5 | 100%
ENG-010 | Metro Regional Transit Authority | Consultant | 2025-08-01 | 117.47 | 159.6 | 135.9% | 24669.24 | 33516 | 33516 | 100%
ENG-010 | Metro Regional Transit Authority | Manager | 2025-08-01 | 42.09 | 64 | 152.1% | 11575.06 | 17600 | 17600 | 100%
ENG-010 | Metro Regional Transit Authority | Partner | 2025-08-01 | 15.59 | 20.8 | 133.4% | 6003.25 | 8008 | 8008 | 100%
ENG-011 | Commonwealth Department of Transportation | Associate | 2025-06-01 | 20.84 | 89 | 427.1% | 3230.71 | 13795 | 13795 | 100%
ENG-011 | Commonwealth Department of Transportation | Consultant | 2025-06-01 | 34.27 | 133 | 388.1% | 7197.58 | 27930 | 29172.5 | 104.4%
ENG-011 | Commonwealth Department of Transportation | Manager | 2025-06-01 | 11.31 | 40.3 | 356.3% | 3109.86 | 11082.5 | 11082.5 | 100%
ENG-011 | Commonwealth Department of Transportation | Partner | 2025-06-01 | 3.67 | 16.1 | 438.7% | 1414.68 | 6198.5 | 6198.5 | 100%
ENG-011 | Commonwealth Department of Transportation | Associate | 2025-07-01 | 27.93 | 227.7 | 815.3% | 4329.85 | 35293.5 | 36157.5 | 102.4%
ENG-011 | Commonwealth Department of Transportation | Consultant | 2025-07-01 | 45.93 | 376.8 | 820.4% | 9646.33 | 79128 | 78985 | 99.82%
ENG-011 | Commonwealth Department of Transportation | Manager | 2025-07-01 | 15.16 | 108.4 | 715% | 4167.89 | 29810 | 30437 | 102.1%
ENG-011 | Commonwealth Department of Transportation | Partner | 2025-07-01 | 4.92 | 33.9 | 689% | 1895.98 | 13051.5 | 13051.5 | 100%
ENG-011 | Commonwealth Department of Transportation | Associate | 2025-08-01 | 34.72 | 89.9 | 258.9% | 5380.96 | 13934.5 | 13934.5 | 100%
ENG-011 | Commonwealth Department of Transportation | Consultant | 2025-08-01 | 57.09 | 137.2 | 240.3% | 11988.06 | 28812 | 28812 | 100%
ENG-011 | Commonwealth Department of Transportation | Manager | 2025-08-01 | 18.84 | 37.8 | 200.6% | 5179.68 | 10395 | 10395 | 100%
ENG-011 | Commonwealth Department of Transportation | Partner | 2025-08-01 | 6.12 | 14 | 228.8% | 2356.25 | 5390 | 5390 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-02-01 | 23.24 | 26.9 | 115.7% | 3601.61 | 4169.5 | 4169.5 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-02-01 | 33.61 | 40.4 | 120.2% | 7057.99 | 8484 | 8484 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-02-01 | 11.26 | 10.9 | 96.8% | 3095.13 | 2997.5 | 3305.5 | 110.3%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-02-01 | 3.99 | 6.3 | 157.9% | 1537.58 | 2425.5 | 2425.5 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-03-01 | 36.24 | 46.1 | 127.2% | 5617.32 | 7145.5 | 7145.5 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-03-01 | 52.42 | 82.9 | 158.1% | 11008.13 | 17409 | 17409 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-03-01 | 17.55 | 27.3 | 155.6% | 4827.38 | 7507.5 | 7507.5 | 100%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-03-01 | 6.23 | 6.2 | 99.52% | 2398.12 | 2387 | 2387 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-04-01 | 47.68 | 77.6 | 162.8% | 7389.9 | 12028 | 12028 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-04-01 | 68.96 | 117.4 | 170.2% | 14481.82 | 24654 | 24654 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-04-01 | 23.09 | 33.5 | 145.1% | 6350.7 | 9212.5 | 8564.5 | 92.97%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-04-01 | 8.19 | 14.6 | 178.3% | 3154.86 | 5621 | 5621 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-05-01 | 56.16 | 97.3 | 173.3% | 8705.56 | 15081.5 | 15081.5 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-05-01 | 81.24 | 107.3 | 132.1% | 17060.09 | 22533 | 22533 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-05-01 | 27.2 | 30.1 | 110.7% | 7481.34 | 8277.5 | 8277.5 | 100%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-05-01 | 9.65 | 15.2 | 157.5% | 3716.54 | 5852 | 5852 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-06-01 | 60.68 | 66.8 | 110.1% | 9405.61 | 10354 | 10354 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-06-01 | 87.77 | 106.9 | 121.8% | 18431.96 | 22449 | 22449 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-06-01 | 29.39 | 42.8 | 145.6% | 8082.95 | 11770 | 11770 | 100%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-06-01 | 10.43 | 14.5 | 139% | 4015.4 | 5582.5 | 5582.5 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-07-01 | 60.68 | 53.9 | 88.83% | 9405.61 | 8354.5 | 8354.5 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-07-01 | 87.77 | 73.3 | 83.51% | 18431.96 | 15393 | 15393 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-07-01 | 29.39 | 23.8 | 80.98% | 8082.95 | 6545 | 6005 | 91.75%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-07-01 | 10.43 | 6.1 | 58.49% | 4015.4 | 2348.5 | 2348.5 | 100%
ENG-012 | Bureau of Health & Human Services | Associate | 2025-08-01 | 56.16 | 33.2 | 59.12% | 8705.56 | 5146 | 5146 | 100%
ENG-012 | Bureau of Health & Human Services | Consultant | 2025-08-01 | 81.24 | 47.8 | 58.84% | 17060.09 | 10038 | 10038 | 100%
ENG-012 | Bureau of Health & Human Services | Manager | 2025-08-01 | 27.2 | 16.4 | 60.29% | 7481.34 | 4510 | 4510 | 100%
ENG-012 | Bureau of Health & Human Services | Partner | 2025-08-01 | 9.65 | 5.8 | 60.1% | 3716.54 | 2233 | 2233 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-02-01 | 24.34 | 18.5 | 76.01% | 3772.41 | 2867.5 | 2867.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-02-01 | 32.27 | 20.3 | 62.91% | 6777.3 | 4263 | 4263 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-02-01 | 12.21 | 11.9 | 97.46% | 3356.99 | 3272.5 | 3272.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-02-01 | 3.74 | 3.4 | 90.91% | 1439.31 | 1309 | 1309 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-03-01 | 44.25 | 44.3 | 100.1% | 6858.93 | 6866.5 | 6866.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-03-01 | 58.68 | 56.8 | 96.8% | 12322.36 | 11928 | 11928 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-03-01 | 22.19 | 22.2 | 100% | 6103.61 | 6105 | 6105 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-03-01 | 6.8 | 2 | 29.41% | 2616.92 | 770 | 770 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-04-01 | 58.83 | 50.8 | 86.35% | 9118.42 | 7874 | 7874 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-04-01 | 78.01 | 74.8 | 95.89% | 16381.63 | 15708 | 15708 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-04-01 | 29.51 | 27.1 | 91.83% | 8114.28 | 7452.5 | 7452.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-04-01 | 9.04 | 8.9 | 98.45% | 3479 | 3426.5 | 3426.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-05-01 | 64.16 | 55.4 | 86.35% | 9945.45 | 8587 | 8587 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-05-01 | 85.08 | 74.2 | 87.21% | 17867.42 | 15582 | 15582 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-05-01 | 32.18 | 25.4 | 78.93% | 8850.24 | 6985 | 6985 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-05-01 | 9.86 | 6.8 | 68.97% | 3794.54 | 2618 | 2618 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-06-01 | 58.83 | 47.6 | 80.91% | 9118.42 | 7378 | 7378 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-06-01 | 78.01 | 58.4 | 74.86% | 16381.63 | 12264 | 12264 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-06-01 | 29.51 | 27.1 | 91.83% | 8114.28 | 7452.5 | 7452.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-06-01 | 9.04 | 9 | 99.56% | 3479 | 3465 | 3465 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-07-01 | 44.25 | 35.7 | 80.68% | 6858.93 | 5533.5 | 5533.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-07-01 | 58.68 | 54.1 | 92.19% | 12322.36 | 11361 | 11361 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-07-01 | 22.19 | 13.7 | 61.74% | 6103.61 | 3767.5 | 3767.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-07-01 | 6.8 | 4.4 | 64.71% | 2616.92 | 1694 | 1694 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Associate | 2025-08-01 | 24.34 | 19.5 | 80.12% | 3772.41 | 3022.5 | 3022.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Consultant | 2025-08-01 | 32.27 | 23.4 | 72.51% | 6777.3 | 4914 | 4914 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Manager | 2025-08-01 | 12.21 | 10.9 | 89.27% | 3356.99 | 2997.5 | 2997.5 | 100%
ENG-013 | Federal Logistics & Readiness Agency | Partner | 2025-08-01 | 3.74 | 3.7 | 98.93% | 1439.31 | 1424.5 | 1424.5 | 100%
ENG-014 | Ashford County Government | Associate | 2025-02-01 | 15.03 | 12 | 79.84% | 2329.67 | 1860 | 1860 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-02-01 | 17.7 | 15.6 | 88.14% | 3717.1 | 3276 | 3276 | 100%
ENG-014 | Ashford County Government | Manager | 2025-02-01 | 8.16 | 3.2 | 39.22% | 2244.98 | 880 | 880 | 100%
ENG-014 | Ashford County Government | Partner | 2025-02-01 | 2.9 | 2.6 | 89.66% | 1116.2 | 1001 | 1001 | 100%
ENG-014 | Ashford County Government | Associate | 2025-03-01 | 27.33 | 18.8 | 68.79% | 4235.77 | 2914 | 2914 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-03-01 | 32.18 | 24.2 | 75.2% | 6758.36 | 5082 | 5082 | 100%
ENG-014 | Ashford County Government | Manager | 2025-03-01 | 14.84 | 11.6 | 78.17% | 4081.79 | 3190 | 3190 | 100%
ENG-014 | Ashford County Government | Partner | 2025-03-01 | 5.27 | 3.3 | 62.62% | 2029.45 | 1270.5 | 1270.5 | 100%
ENG-014 | Ashford County Government | Associate | 2025-04-01 | 36.33 | 26.9 | 74.04% | 5631.13 | 4169.5 | 4169.5 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-04-01 | 42.78 | 30.8 | 72% | 8984.72 | 6468 | 6468 | 100%
ENG-014 | Ashford County Government | Manager | 2025-04-01 | 19.73 | 11.9 | 60.31% | 5426.43 | 3272.5 | 3272.5 | 100%
ENG-014 | Ashford County Government | Partner | 2025-04-01 | 7.01 | 5.2 | 74.18% | 2698 | 2002 | 2002 | 100%
ENG-014 | Ashford County Government | Associate | 2025-05-01 | 39.62 | 34.9 | 88.09% | 6141.86 | 5409.5 | 5409.5 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-05-01 | 46.66 | 36.3 | 77.8% | 9799.63 | 7623 | 7623 | 100%
ENG-014 | Ashford County Government | Manager | 2025-05-01 | 21.52 | 13.4 | 62.27% | 5918.6 | 3685 | 3685 | 100%
ENG-014 | Ashford County Government | Partner | 2025-05-01 | 7.64 | 3.6 | 47.12% | 2942.7 | 1386 | 1386 | 100%
ENG-014 | Ashford County Government | Associate | 2025-06-01 | 36.33 | 26.4 | 72.67% | 5631.13 | 4092 | 4092 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-06-01 | 42.78 | 35.9 | 83.92% | 8984.72 | 7539 | 7883.5 | 104.6%
ENG-014 | Ashford County Government | Manager | 2025-06-01 | 19.73 | 15.9 | 80.59% | 5426.43 | 4372.5 | 4372.5 | 100%
ENG-014 | Ashford County Government | Partner | 2025-06-01 | 7.01 | 4.5 | 64.19% | 2698 | 1732.5 | 1732.5 | 100%
ENG-014 | Ashford County Government | Associate | 2025-07-01 | 27.33 | 16 | 58.54% | 4235.77 | 2480 | 2480 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-07-01 | 32.18 | 23.5 | 73.03% | 6758.36 | 4935 | 4935 | 100%
ENG-014 | Ashford County Government | Manager | 2025-07-01 | 14.84 | 8.4 | 56.6% | 4081.79 | 2310 | 2310 | 100%
ENG-014 | Ashford County Government | Partner | 2025-07-01 | 5.27 | 4.6 | 87.29% | 2029.45 | 1771 | 1771 | 100%
ENG-014 | Ashford County Government | Associate | 2025-08-01 | 15.03 | 8.8 | 58.55% | 2329.67 | 1364 | 1364 | 100%
ENG-014 | Ashford County Government | Consultant | 2025-08-01 | 17.7 | 15.6 | 88.14% | 3717.1 | 3276 | 3276 | 100%
ENG-014 | Ashford County Government | Manager | 2025-08-01 | 8.16 | 6.5 | 79.66% | 2244.98 | 1787.5 | 1787.5 | 100%
ENG-014 | Ashford County Government | Partner | 2025-08-01 | 2.9 | 2.6 | 89.66% | 1116.2 | 1001 | 1001 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2024-12-01 | 27.88 | 36.6 | 131.3% | 4321.12 | 5673 | 5673 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2024-12-01 | 35.7 | 50 | 140.1% | 7497.63 | 10500 | 10500 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2024-12-01 | 11.03 | 11.3 | 102.4% | 3032.57 | 3107.5 | 3107.5 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2024-12-01 | 3.71 | 6.4 | 172.5% | 1429.21 | 2464 | 2464 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-01-01 | 38.8 | 57.7 | 148.7% | 6013.3 | 8943.5 | 8943.5 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-01-01 | 49.68 | 67.7 | 136.3% | 10433.76 | 14217 | 14217 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-01-01 | 15.35 | 15.9 | 103.6% | 4220.15 | 4372.5 | 4372.5 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-01-01 | 5.17 | 10.4 | 201.2% | 1988.9 | 4004 | 4004 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-02-01 | 49.08 | 87.3 | 177.9% | 7607.14 | 13531.5 | 13531.5 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-02-01 | 62.85 | 111.7 | 177.7% | 13199.26 | 23457 | 23457 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-02-01 | 19.41 | 39 | 200.9% | 5338.71 | 10725 | 10725 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-02-01 | 6.54 | 10.9 | 166.7% | 2516.07 | 4196.5 | 4196.5 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-03-01 | 58.13 | 115.8 | 199.2% | 9010.01 | 17949 | 17949 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-03-01 | 74.44 | 132.8 | 178.4% | 15633.39 | 27888 | 28815.5 | 103.3%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-03-01 | 22.99 | 38.6 | 167.9% | 6323.25 | 10615 | 10615 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-03-01 | 7.74 | 14.9 | 192.5% | 2980.07 | 5736.5 | 5736.5 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-04-01 | 65.42 | 107.6 | 164.5% | 10140.38 | 16678 | 16678 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-04-01 | 83.78 | 123.2 | 147.1% | 17594.7 | 25872 | 25542 | 98.72%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-04-01 | 25.88 | 42.8 | 165.4% | 7116.54 | 11770 | 11770 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-04-01 | 8.71 | 12.8 | 147% | 3353.93 | 4928 | 4928 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-05-01 | 70.53 | 107.2 | 152% | 10932.55 | 16616 | 16616 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-05-01 | 90.33 | 135.5 | 150% | 18969.21 | 28455 | 28455 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-05-01 | 27.9 | 38.5 | 138% | 7672.49 | 10587.5 | 10587.5 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-05-01 | 9.39 | 16.1 | 171.5% | 3615.95 | 6198.5 | 6198.5 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-06-01 | 73.16 | 90.3 | 123.4% | 11340.49 | 13996.5 | 13996.5 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-06-01 | 93.7 | 112.1 | 119.6% | 19677.04 | 23541 | 24661 | 104.8%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-06-01 | 28.94 | 41 | 141.7% | 7958.78 | 11275 | 11275 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-06-01 | 9.74 | 12.1 | 124.2% | 3750.87 | 4658.5 | 4658.5 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-07-01 | 73.16 | 62.8 | 85.84% | 11340.49 | 9734 | 9734 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-07-01 | 93.7 | 74.3 | 79.3% | 19677.04 | 15603 | 15603 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-07-01 | 28.94 | 20.4 | 70.49% | 7958.78 | 5610 | 5610 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-07-01 | 9.74 | 9.7 | 99.59% | 3750.87 | 3734.5 | 3734.5 | 100%
ENG-015 | Metro Regional Transit Authority | Associate | 2025-08-01 | 70.53 | 36.7 | 52.03% | 10932.55 | 5688.5 | 5688.5 | 100%
ENG-015 | Metro Regional Transit Authority | Consultant | 2025-08-01 | 90.33 | 50 | 55.35% | 18969.21 | 10500 | 10500 | 100%
ENG-015 | Metro Regional Transit Authority | Manager | 2025-08-01 | 27.9 | 11.8 | 42.29% | 7672.49 | 3245 | 3245 | 100%
ENG-015 | Metro Regional Transit Authority | Partner | 2025-08-01 | 9.39 | 5.5 | 58.57% | 3615.95 | 2117.5 | 2117.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2024-10-01 | 25.21 | 18.3 | 72.59% | 3907.1 | 2836.5 | 2836.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2024-10-01 | 32.05 | 23.7 | 73.95% | 6731.23 | 4977 | 4977 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2024-10-01 | 10.79 | 10.8 | 100.1% | 2966.76 | 2970 | 2970 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2024-10-01 | 4.51 | 4.5 | 99.78% | 1737.27 | 1732.5 | 1732.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2024-11-01 | 39.31 | 29.5 | 75.04% | 6093.79 | 4572.5 | 4572.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2024-11-01 | 49.99 | 40.6 | 81.22% | 10498.49 | 8526 | 8526 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2024-11-01 | 16.83 | 15.4 | 91.5% | 4627.17 | 4235 | 4235 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2024-11-01 | 7.04 | 4.5 | 63.92% | 2709.56 | 1732.5 | 1732.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2024-12-01 | 51.72 | 39.5 | 76.37% | 8016.72 | 6122.5 | 6122.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2024-12-01 | 65.77 | 57.2 | 86.97% | 13811.37 | 12012 | 12449.5 | 103.6%
ENG-016 | Commonwealth Department of Transportation | Manager | 2024-12-01 | 22.14 | 22.1 | 99.82% | 6087.3 | 6077.5 | 6077.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2024-12-01 | 9.26 | 5.8 | 62.63% | 3564.58 | 2233 | 2233 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-01-01 | 60.93 | 38.6 | 63.35% | 9443.98 | 5983 | 5983 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-01-01 | 77.48 | 59.6 | 76.92% | 16270.28 | 12516 | 12516 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-01-01 | 26.08 | 23.1 | 88.57% | 7171.06 | 6352.5 | 6352.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-01-01 | 10.91 | 7.1 | 65.08% | 4199.21 | 2733.5 | 2733.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-02-01 | 65.83 | 45.7 | 69.42% | 10203.41 | 7083.5 | 7083.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-02-01 | 83.71 | 69.4 | 82.91% | 17578.63 | 14574 | 14574 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-02-01 | 28.17 | 28.2 | 100.1% | 7747.71 | 7755 | 7755 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-02-01 | 11.78 | 9.6 | 81.49% | 4536.88 | 3696 | 3696 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-03-01 | 65.83 | 53.9 | 81.88% | 10203.41 | 8354.5 | 8354.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-03-01 | 83.71 | 77.5 | 92.58% | 17578.63 | 16275 | 16275 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-03-01 | 28.17 | 23.4 | 83.07% | 7747.71 | 6435 | 6435 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-03-01 | 11.78 | 11.8 | 100.2% | 4536.88 | 4543 | 4543 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-04-01 | 60.93 | 57.1 | 93.71% | 9443.98 | 8850.5 | 8850.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-04-01 | 77.48 | 62.3 | 80.41% | 16270.28 | 13083 | 13083 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-04-01 | 26.08 | 23.7 | 90.87% | 7171.06 | 6517.5 | 6517.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-04-01 | 10.91 | 10.9 | 99.91% | 4199.21 | 4196.5 | 4196.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-05-01 | 51.72 | 40.6 | 78.5% | 8016.72 | 6293 | 7420 | 117.9%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-05-01 | 65.77 | 56.9 | 86.51% | 13811.37 | 11949 | 11949 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-05-01 | 22.14 | 20.1 | 90.79% | 6087.3 | 5527.5 | 5527.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-05-01 | 9.26 | 9.3 | 100.4% | 3564.58 | 3580.5 | 3580.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-06-01 | 39.31 | 38.8 | 98.7% | 6093.79 | 6014 | 6014 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-06-01 | 49.99 | 30.6 | 61.21% | 10498.49 | 6426 | 6426 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-06-01 | 16.83 | 15.4 | 91.5% | 4627.17 | 4235 | 4235 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-06-01 | 7.04 | 6.2 | 88.07% | 2709.56 | 2387 | 2387 | 100%
ENG-016 | Commonwealth Department of Transportation | Associate | 2025-07-01 | 25.21 | 19.3 | 76.56% | 3907.1 | 2991.5 | 2991.5 | 100%
ENG-016 | Commonwealth Department of Transportation | Consultant | 2025-07-01 | 32.05 | 19.1 | 59.59% | 6731.23 | 4011 | 4011 | 100%
ENG-016 | Commonwealth Department of Transportation | Manager | 2025-07-01 | 10.79 | 6.2 | 57.46% | 2966.76 | 1705 | 1705 | 100%
ENG-016 | Commonwealth Department of Transportation | Partner | 2025-07-01 | 4.51 | 4.5 | 99.78% | 1737.27 | 1732.5 | 1732.5 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-01-01 | 12.09 | 15.5 | 128.2% | 1874.68 | 2402.5 | 2402.5 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-01-01 | 16.74 | 18.7 | 111.7% | 3514.51 | 3927 | 3927 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-01-01 | 6.33 | 3.9 | 61.61% | 1740.38 | 1072.5 | 1072.5 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-01-01 | 2.58 | 3.6 | 139.5% | 992.66 | 1386 | 1386 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-02-01 | 18.21 | 27.6 | 151.6% | 2822.64 | 4278 | 4278 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-02-01 | 25.2 | 38.9 | 154.4% | 5291.66 | 8169 | 8604.5 | 105.3%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-02-01 | 9.53 | 13.9 | 145.9% | 2620.42 | 3822.5 | 3822.5 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-02-01 | 3.88 | 5.3 | 136.6% | 1494.61 | 2040.5 | 2040.5 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-03-01 | 23.73 | 32 | 134.9% | 3677.81 | 4960 | 4960 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-03-01 | 32.83 | 46.7 | 142.2% | 6894.86 | 9807 | 9807 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-03-01 | 12.42 | 15.1 | 121.6% | 3414.32 | 4152.5 | 4152.5 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-03-01 | 5.06 | 2.2 | 43.48% | 1947.43 | 847 | 847 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-04-01 | 28.11 | 36.1 | 128.4% | 4356.48 | 5595.5 | 5595.5 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-04-01 | 38.89 | 44.2 | 113.7% | 8167.17 | 9282 | 9282 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-04-01 | 14.71 | 23.1 | 157% | 4044.37 | 6352.5 | 6352.5 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-04-01 | 5.99 | 9.4 | 156.9% | 2306.79 | 3619 | 3619 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-05-01 | 30.92 | 28 | 90.56% | 4792.21 | 4340 | 4340 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-05-01 | 42.78 | 37.8 | 88.36% | 8984.04 | 7938 | 7938 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-05-01 | 16.18 | 20.5 | 126.7% | 4448.88 | 5637.5 | 5637.5 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-05-01 | 6.59 | 9.4 | 142.6% | 2537.51 | 3619 | 3619 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-06-01 | 31.89 | 33.9 | 106.3% | 4942.35 | 5254.5 | 5254.5 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-06-01 | 44.12 | 44.7 | 101.3% | 9265.51 | 9387 | 9387 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-06-01 | 16.68 | 20.3 | 121.7% | 4588.26 | 5582.5 | 6385.5 | 114.4%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-06-01 | 6.8 | 4.1 | 60.29% | 2617.01 | 1578.5 | 1578.5 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-07-01 | 30.92 | 20.2 | 65.33% | 4792.21 | 3131 | 3131 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-07-01 | 42.78 | 35.6 | 83.22% | 8984.04 | 7476 | 7476 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-07-01 | 16.18 | 15.2 | 93.94% | 4448.88 | 4180 | 4180 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-07-01 | 6.59 | 3.6 | 54.63% | 2537.51 | 1386 | 1386 | 100%
ENG-017 | Bureau of Health & Human Services | Associate | 2025-08-01 | 28.11 | 17 | 60.48% | 4356.48 | 2635 | 2635 | 100%
ENG-017 | Bureau of Health & Human Services | Consultant | 2025-08-01 | 38.89 | 20.4 | 52.46% | 8167.17 | 4284 | 4284 | 100%
ENG-017 | Bureau of Health & Human Services | Manager | 2025-08-01 | 14.71 | 4.2 | 28.55% | 4044.37 | 1155 | 1155 | 100%
ENG-017 | Bureau of Health & Human Services | Partner | 2025-08-01 | 5.99 | 3.6 | 60.1% | 2306.79 | 1386 | 1386 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-02-01 | 14.95 | 9.2 | 61.54% | 2317.85 | 1426 | 1426 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-02-01 | 21.44 | 21.4 | 99.81% | 4502.18 | 4494 | 4494 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-02-01 | 6.87 | 6.6 | 96.07% | 1888.31 | 1815 | 1815 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-02-01 | 2.75 | 2.7 | 98.18% | 1057.45 | 1039.5 | 1039.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-03-01 | 27.19 | 26.2 | 96.36% | 4214.27 | 4061 | 4061 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-03-01 | 38.98 | 31.7 | 81.32% | 8185.78 | 6657 | 6657 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-03-01 | 12.48 | 5.7 | 45.67% | 3433.28 | 1567.5 | 1567.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-03-01 | 4.99 | 3.7 | 74.15% | 1922.64 | 1424.5 | 1424.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-04-01 | 36.15 | 27.9 | 77.18% | 5602.54 | 4324.5 | 4324.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-04-01 | 51.82 | 45.3 | 87.42% | 10882.36 | 9513 | 9513 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-04-01 | 16.6 | 14.2 | 85.54% | 4564.28 | 3905 | 3905 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-04-01 | 6.64 | 5.1 | 76.81% | 2556 | 1963.5 | 1963.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-05-01 | 39.42 | 39.4 | 99.95% | 6110.69 | 6107 | 6107 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-05-01 | 56.52 | 41.7 | 73.78% | 11869.38 | 8757 | 8757 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-05-01 | 18.1 | 15.9 | 87.85% | 4978.26 | 4372.5 | 4372.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-05-01 | 7.24 | 4.5 | 62.15% | 2787.82 | 1732.5 | 1732.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-06-01 | 36.15 | 29.6 | 81.88% | 5602.54 | 4588 | 4588 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-06-01 | 51.82 | 44.1 | 85.1% | 10882.36 | 9261 | 9261 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-06-01 | 16.6 | 15.6 | 93.98% | 4564.28 | 4290 | 4290 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-06-01 | 6.64 | 5.9 | 88.86% | 2556 | 2271.5 | 2271.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-07-01 | 27.19 | 20.1 | 73.92% | 4214.27 | 3115.5 | 3115.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-07-01 | 38.98 | 25.7 | 65.93% | 8185.78 | 5397 | 5397 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-07-01 | 12.48 | 7.8 | 62.5% | 3433.28 | 2145 | 2145 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-07-01 | 4.99 | 4.5 | 90.18% | 1922.64 | 1732.5 | 1732.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Associate | 2025-08-01 | 14.95 | 11.2 | 74.92% | 2317.85 | 1736 | 1736 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Consultant | 2025-08-01 | 21.44 | 20.1 | 93.75% | 4502.18 | 4221 | 4221 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Manager | 2025-08-01 | 6.87 | 3.1 | 45.12% | 1888.31 | 852.5 | 852.5 | 100%
ENG-018 | Federal Logistics & Readiness Agency | Partner | 2025-08-01 | 2.75 | 2.7 | 98.18% | 1057.45 | 1039.5 | 1039.5 | 100%

## Sample Invoice
Meridian Advisory Partners
1200 Market Street, Suite 900, Washington, DC 20005
CLIENT INVOICE
DRAFT -- pending engagement leader review
Invoice #: | INV-ENG-010-202507 |  | Invoice Date: | 2025-08-05
Bill To: | Metro Regional Transit Authority |  | Billing Period: | 2025-07-01 to 2025-07-31
Engagement: | Fare System Financial Reconciliation Support |  | Engagement ID: | ENG-010
Contract Type: | Time & Materials |  | Engagement Leader: | S. Whitfield
Description | Category | Role | Hours | Rate | Amount
Professional Services -- Partner | Labor | Partner | 54.5 | 385 | 20982.5
Professional Services -- Manager | Labor | Manager | 141.9 | 275 | 39022.5
Professional Services -- Consultant | Labor | Consultant | 377.1 | 210 | 79191
Professional Services -- Associate | Labor | Associate | 287 | 155 | 44485
Reimbursable Expenses -- Ground Transport | Expense |  |  |  | 89.73
Subtotal -- Labor |  |  |  |  | 183681
Subtotal -- Expenses |  |  |  |  | 89.73
TOTAL AMOUNT DUE |  |  |  |  | 183770.73
This draft invoice reflects hours and expenses recorded as approved and correctly coded in the firm's timekeeping system as of the billing period close. Every line item traces back to specific timesheet/expense records; see reconcile_invoice_to_source() in invoicing.py.

## Discrepancy Report
Discrepancy & Exception Report
Prioritized by severity, then dollar impact -- as of 2025-08-15. Synthetic data for demonstration only.
Discrepancy ID | Engagement ID | Client | Engagement Leader | Category | Severity | Dollar Impact | Description | Recommended Action | Detected Date | Escalation Summary by Engagement Leader
DQ-UNBILL-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Unbilled Time Aging | High | 79722 | $79,722.00 of approved, billable time (369.2 hrs) has not been invoiced, oldest entry 106 days old. | Include in next billing cycle; if a prior invoice run missed this work, investigate why. | 2025-08-15 | Leader | Open Exceptions | High | Medium | Low | Total $ Impact | Engagements Affected
DQ-UNBILL-ENG-018 | ENG-018 | Federal Logistics & Readiness Agency | J. Patel | Unbilled Time Aging | High | 20410.5 | $20,410.50 of approved, billable time (95.2 hrs) has not been invoiced, oldest entry 73 days old. | Include in next billing cycle; if a prior invoice run missed this work, investigate why. | 2025-08-15 | R. Chen | 28 | 7 | 14 | 7 | 80911.5 | 7
DQ-APPR-ENG-006 | ENG-006 | Commonwealth Department of Transportation | R. Chen | Missing Approval | High | 6656 | 5 time entries are unapproved, oldest 205 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15 | J. Patel | 8 | 4 | 2 | 2 | 38263.62 | 3
DQ-APPR-ENG-012 | ENG-012 | Bureau of Health & Human Services | R. Chen | Missing Approval | High | 5623 | 6 time entries are unapproved, oldest 127 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15 | D. Okoro | 10 | 3 | 4 | 3 | 112927.06 | 2
DQ-APPR-ENG-010 | ENG-010 | Metro Regional Transit Authority | S. Whitfield | Missing Approval | High | 5460 | 5 time entries are unapproved, oldest 77 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15 | M. Alvarez | 10 | 3 | 4 | 3 | 28838.5 | 3
DQ-APPR-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Missing Approval | High | 5272 | 5 time entries are unapproved, oldest 247 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15 | S. Whitfield | 8 | 2 | 4 | 2 | 78698.14 | 2
DQ-APPR-ENG-015 | ENG-015 | Metro Regional Transit Authority | R. Chen | Missing Approval | High | 5127.5 | 4 time entries are unapproved, oldest 200 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-011 | ENG-011 | Commonwealth Department of Transportation | J. Patel | Missing Approval | High | 3861.5 | 4 time entries are unapproved, oldest 74 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-003 | ENG-003 | Federal Logistics & Readiness Agency | M. Alvarez | Missing Approval | High | 3148.5 | 4 time entries are unapproved, oldest 51 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-016 | ENG-016 | Commonwealth Department of Transportation | D. Okoro | Missing Approval | High | 2734 | 3 time entries are unapproved, oldest 163 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-008 | ENG-008 | Federal Logistics & Readiness Agency | R. Chen | Missing Approval | High | 2612.5 | 3 time entries are unapproved, oldest 86 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-004 | ENG-004 | Ashford County Government | M. Alvarez | Missing Approval | High | 2436 | 2 time entries are unapproved, oldest 282 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-001 | ENG-001 | Commonwealth Department of Transportation | M. Alvarez | Missing Approval | High | 2233 | 1 time entry is unapproved, oldest 190 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-002 | ENG-002 | Bureau of Health & Human Services | R. Chen | Missing Approval | High | 1848 | 2 time entries are unapproved, oldest 108 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-013 | ENG-013 | Federal Logistics & Readiness Agency | J. Patel | Missing Approval | High | 1821 | 2 time entries are unapproved, oldest 74 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-017 | ENG-017 | Bureau of Health & Human Services | S. Whitfield | Missing Approval | High | 1119.5 | 2 time entries are unapproved, oldest 128 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-014 | ENG-014 | Ashford County Government | R. Chen | Missing Approval | High | 1045 | 1 time entry is unapproved, oldest 88 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-018 | ENG-018 | Federal Logistics & Readiness Agency | J. Patel | Missing Approval | High | 821.5 | 2 time entries are unapproved, oldest 128 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-APPR-ENG-005 | ENG-005 | Metro Regional Transit Authority | R. Chen | Missing Approval | High | 687.5 | 1 time entry is unapproved, oldest 52 days past the work date (normal cycle is 14 days). | Escalate to approving manager for immediate sign-off; time cannot be billed until approved. | 2025-08-15
DQ-CODE-ENG-006 | ENG-006 | Commonwealth Department of Transportation | R. Chen | Missing Task Code | Medium | 13679 | 9 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Missing Task Code | Medium | 9057.5 | 8 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-010 | ENG-010 | Metro Regional Transit Authority | S. Whitfield | Missing Task Code | Medium | 5631 | 5 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-014 | ENG-014 | Ashford County Government | R. Chen | Missing Task Code | Medium | 3979 | 3 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-002 | ENG-002 | Bureau of Health & Human Services | R. Chen | Missing Task Code | Medium | 3759.5 | 4 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-005 | ENG-005 | Metro Regional Transit Authority | R. Chen | Missing Task Code | Medium | 3712.5 | 3 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-001 | ENG-001 | Commonwealth Department of Transportation | M. Alvarez | Missing Task Code | Medium | 2936 | 4 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-016 | ENG-016 | Commonwealth Department of Transportation | D. Okoro | Missing Task Code | Medium | 2744.5 | 4 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-RATE-ENG-011 | ENG-011 | Commonwealth Department of Transportation | J. Patel | Rate Mismatch | Medium | 2590.5 | 4 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $2,590.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-CODE-ENG-015 | ENG-015 | Metro Regional Transit Authority | R. Chen | Missing Task Code | Medium | 2108 | 2 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-012 | ENG-012 | Bureau of Health & Human Services | R. Chen | Missing Task Code | Medium | 1963 | 2 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-013 | ENG-013 | Federal Logistics & Readiness Agency | J. Patel | Missing Task Code | Medium | 1925 | 1 timesheet entry is missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-CODE-ENG-004 | ENG-004 | Ashford County Government | M. Alvarez | Missing Task Code | Medium | 1849.5 | 2 timesheet entries are missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-RATE-ENG-015 | ENG-015 | Metro Regional Transit Authority | R. Chen | Rate Mismatch | Medium | 1717.5 | 3 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $1,717.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-016 | ENG-016 | Commonwealth Department of Transportation | D. Okoro | Rate Mismatch | Medium | 1564.5 | 2 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $1,564.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-006 | ENG-006 | Commonwealth Department of Transportation | R. Chen | Rate Mismatch | Medium | 1520 | 7 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $-1,520.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-CODE-ENG-017 | ENG-017 | Bureau of Health & Human Services | S. Whitfield | Missing Task Code | Medium | 1240 | 1 timesheet entry is missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-RATE-ENG-017 | ENG-017 | Bureau of Health & Human Services | S. Whitfield | Rate Mismatch | Medium | 1238.5 | 2 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $1,238.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-001 | ENG-001 | Commonwealth Department of Transportation | M. Alvarez | Rate Mismatch | Medium | 1206.5 | 3 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $1,206.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-004 | ENG-004 | Ashford County Government | M. Alvarez | Rate Mismatch | Medium | 1032 | 3 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $1,032.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-010 | ENG-010 | Metro Regional Transit Authority | S. Whitfield | Rate Mismatch | Medium | 885.5 | 9 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $885.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-012 | ENG-012 | Bureau of Health & Human Services | R. Chen | Rate Mismatch | Medium | 880 | 3 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $-880.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-002 | ENG-002 | Bureau of Health & Human Services | R. Chen | Rate Mismatch | Medium | 649 | 1 entry is logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $649.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-008 | ENG-008 | Federal Logistics & Readiness Agency | R. Chen | Rate Mismatch | Medium | 595 | 1 entry is logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $595.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-CODE-ENG-008 | ENG-008 | Federal Logistics & Readiness Agency | R. Chen | Missing Task Code | Medium | 511.5 | 1 timesheet entry is missing a task code and cannot be routed to billing. | Return to timekeeper for task code correction, then re-submit for approval and billing. | 2025-08-15
DQ-RATE-ENG-005 | ENG-005 | Metro Regional Transit Authority | R. Chen | Rate Mismatch | Medium | 440 | 3 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $440.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Rate Mismatch | Medium | 392 | 7 entries are logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $392.00). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-RATE-ENG-014 | ENG-014 | Ashford County Government | R. Chen | Rate Mismatch | Medium | 344.5 | 1 entry is logged at a labor rate that doesn't match the standard rate card for the recorded role (net rate variance $344.50). | Confirm correct labor category with resource manager and correct the rate before invoicing. | 2025-08-15
DQ-NEARCEIL-ENG-010 | ENG-010 | Metro Regional Transit Authority | S. Whitfield | Approaching Budget Ceiling | Low | 57669.14 | Actual spend ($529,438.00) has reached 90% of the authorized ceiling ($587,107.14). | Monitor closely; discuss scope/change-order runway with engagement leader before ceiling is reached. | 2025-08-15
DQ-OOP-ENG-005 | ENG-005 | Metro Regional Transit Authority | R. Chen | Out-of-Period Entry | Low | 10008.5 | 8 time entries were logged 87 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Out-of-Period Entry | Low | 6411.5 | 6 time entries were logged 66 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-011 | ENG-011 | Commonwealth Department of Transportation | J. Patel | Out-of-Period Entry | Low | 5629.5 | 4 time entries were logged 80 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-010 | ENG-010 | Metro Regional Transit Authority | S. Whitfield | Out-of-Period Entry | Low | 5454.5 | 4 time entries were logged 80 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-003 | ENG-003 | Federal Logistics & Readiness Agency | M. Alvarez | Out-of-Period Entry | Low | 5246 | 4 time entries were logged 75 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-016 | ENG-016 | Commonwealth Department of Transportation | D. Okoro | Out-of-Period Entry | Low | 4620 | 2 time entries were logged 47 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-004 | ENG-004 | Ashford County Government | M. Alvarez | Out-of-Period Entry | Low | 4432 | 6 time entries were logged 84 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-001 | ENG-001 | Commonwealth Department of Transportation | M. Alvarez | Out-of-Period Entry | Low | 4319 | 3 time entries were logged 50 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-002 | ENG-002 | Bureau of Health & Human Services | R. Chen | Out-of-Period Entry | Low | 3780 | 3 time entries were logged 78 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-006 | ENG-006 | Commonwealth Department of Transportation | R. Chen | Out-of-Period Entry | Low | 2778 | 3 time entries were logged 88 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-015 | ENG-015 | Metro Regional Transit Authority | R. Chen | Out-of-Period Entry | Low | 2093.5 | 2 time entries were logged 65 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-012 | ENG-012 | Bureau of Health & Human Services | R. Chen | Out-of-Period Entry | Low | 1314.5 | 2 time entries were logged 44 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-UNBILLEXP-ENG-018 | ENG-018 | Federal Logistics & Readiness Agency | J. Patel | Unbilled Expense Aging | Low | 1204.12 | $1,204.12 of approved, billable expenses have not been invoiced (oldest 73 days). | Include in next billing cycle. | 2025-08-15
DQ-OOP-ENG-014 | ENG-014 | Ashford County Government | R. Chen | Out-of-Period Entry | Low | 1045 | 1 time entry was logged 88 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-OOP-ENG-008 | ENG-008 | Federal Logistics & Readiness Agency | R. Chen | Out-of-Period Entry | Low | 434 | 1 time entry was logged 59 days after the work date at worst (policy threshold is 21 days). | Reinforce weekly timesheet submission policy with team; review affected months for reporting accuracy. | 2025-08-15
DQ-UNBILLEXP-ENG-009 | ENG-009 | Ashford County Government | D. Okoro | Unbilled Expense Aging | Low | 409.06 | $409.06 of approved, billable expenses have not been invoiced (oldest 99 days). | Include in next billing cycle. | 2025-08-15